## Slide 1
SOFTWARE TESTING

## Slide 2
Software Test Planning

## Slide 3
Software test planning is the process of evolving a software test plan which discusses what, when and how testing has to be done as part of the project to ensure quality expectations of the product can be met.
The out come also serves as a blueprint to conduct software testing activities as a defined process
Developers, business managers and customers can understand the details of testing
This can also be used for monitoring and control.
This software test planning process involves
  Ensuring the context and the scope of the project/product under test is well understood
  Establishment of the test adequacy criteria
Generics

## Slide 4
Software test planning process involves (Contd.)
  Evolving a test strategy which will be followed for satisfying the objectives for testing (this was discussed in the earlier session)
  Evolving a list of deliverables
  Creation of detailed test schedule (including estimation of test cases, effort involved for set-up, execution etc.)
  Planning, Identification and Allocation of resources (people, hardware, software, laboratory, tools, money) needed for testing the project/product
  Identification of the milestones which will be considered
  Risk management for the testing activity
  Establishment of measures & metrics for the project.
Generics

## Slide 5
  This involves understand the context where the product is going to be used by
    Reviewing the use case scenario in the product deployment environment
    Discussing with the designer (Interviews/Meetings)
    Discussing with the developer
    Reviewing project/product documentation
    Play around the product or perform product walk-through
  Given that products and project software components have zillions of combinations its not feasible and practical to exhaustively test all of those different combinations with all of those different techniques for testing.
1. Understanding and determining the product testing scope

## Slide 6
  An optimal amount of testing will need to be done, which would mean a subset of the combinations, which would be based on
    The customer requirement (based on product domain, criticality of the product, its risk assessment and the quality criteria’s expected)
    Project Schedule
    Project Budget
    Product Specification
    Skills & talent of your test team
  At the end of this, there needs to be a clear scope in terms of what would be "in scope" and "out of scope" of the testing.
1. Understanding and determining the product testing scope (Cont.)
Notes: https://www.guru99.com/what-everybody-ought-to-know-about-test-planing.html
https://www.softwaretestingmentor.com/what-is-test-planning/
https://www.tutorialspoint.com/software_testing_dictionary/test_plan.htm
https://www.softwaretestinghelp.com/software-development-testing-methodologies/

## Slide 7: 2. Test Adequacy
This testing of the subset of possible combinations does not guarantee absence of issues.
There could also be issues found during testing, all of which may not be feasible to be closed immediately before releasing to customer, due to constraints in terms of
  No of errors which have been found
  Schedule not permitting it to be fixed
  Resources (people, equipment, money) available for fixing the same
  Some of the issues may be more enhancements
This leads to Test Adequacy criteria which describes the criteria which can be used for determining when to stop testing or consider testing to be complete for that iteration.

## Slide 8: 2. Test Adequacy (Cont.)
This criteria could be a combination of criteria's like
  All planned tests are completed and post that based on the % of lines of code, or the % of branches, executed .. etc. when the test cases are run
    E.g. - 100% of the statements have been exercised - 85% of the branches have been exercised
  All planned test cases are completed and when there are no Critical high priority issues pending to be fixed
  It could be when the total number of Severe defects are less than 5 and they are not causing data corruption or stoppage of service
  Etc.

## Slide 9: 4. Evolving a list of deliverable
In this step the list of activities and deliverables will be identified which would need to executed and delivered.
This could include test specifications for each of the modules of the product, test cases for different conditions planned.

## Slide 10: 5. Creation of detailed test schedule
This including estimation for building test strategy/specification/test cases/test environment setup and test execution, test reporting etc.)
This would include WBS and estimation using some of the techniques used earlier (similar to project planning).
This would lead to something like Create test scenarios and test cases - 100 man hours
Execute test cases - 200 man hours
………..
We would associate the same into a calendar

## Slide 11: 6. Planning, Identification and Allocation of resources
This and the previous step of estimating and scheduling are done together or iterated to ensure that the schedule factors in the characteristics of the planned resources.
Initially this will involve
  Identifying the number and type of servers, storage, test tools and the network resources needed for the activities identified
  Identifying the number and type of people to work on the project. This could be in the roles of test manager, testers, test developers, test administrators and SQA with the requisite skills and skill level.
  Identifying the test environment (test rings etc.) which would be set up with the resources identified along with identification of the test data sets etc.

## Slide 12: 7 & 8 : Identification of the milestones & Risks
Once the resources are identified and their capacities, skills are identified, the schedule is reworked.
Considering the deliverables expected, the schedule and commitments if any to the customers, the project milestones are identified.
Risks for completion of each of the task from a schedule and quality perspective is identified, analyzed, mitigation plans made and the triggers for kick-off identified.
These milestones are used to track or monitor progress and control overruns. These milestones are also used to identify any risk triggers and to help kick-in the mitigation plans.

## Slide 13: 9 : Measures are identified and Metrics identified
The measurements which will be made like the number of test cases planned and created, number of test cases run, the amount of time spent on creation, execution, the number of errors found etc.
The errors are classified as per define policies on whether they are critical, serious, medium or low impact.
Metrics like the number of test cases executed/day or % of test cases executed to planned, number of issues/KLoC, number of critical issues/KLoC are planned for measurement and evaluation, No of requirements traced across the lifecycle etc.